## Blad1
Building number | Name | Construction phase | Total number of appartments | Type | Number
1 | Ferme de la Fot | Existing building 70% level | 9 | Studio | 3
|  | SOLD |  | 1 bedroom | 3
|  | Refurb in progress |  | 2 bedroom | 2
|  |  |  | 3 bedroom | 1
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
2 | Colonie | Existing building | 12 | Studio | 0
|  | refurb not started |  | 1 bedroom | 0
|  | available to sell |  | 2 bedroom | 6
|  |  |  | 3 bedroom | 6
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
3 | Maison du Garde | Existing building | 2 | Studio | 0
|  | refurb not started |  | 1 bedroom | 0
|  | SOLD |  | 2 bedroom | 0
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 1
|  |  |  | 4 bedroom semi detached | 1
|  |  |  | Treehouse | 0
4 | Maison des Metiers | Existing building | 4 | Studio | 0
|  | Refurb complete |  | 1 bedroom | 0
|  | SOLD |  | 2 bedroom | 4
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
7 | Maison de l'horloge | Existing Building | 10 | Studio | 0
|  | roof level 70% |  | 1 bedroom | 0
|  | SOLD |  | 2 bedroom | 10
|  | refurb in progress |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
A | RENOIR | NEW BUILD | 25 | Studio | 7
|  | ROOF LEVEL 70% BUILD |  | 1 bedroom | 7
|  | NEARLY SOLD OUT |  | 2 bedroom | 11
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
B | Monet | New Build | 12 | Studio | 0
|  | SOLD |  | 1 bedroom | 0
|  | 70% ROOF LEVEL |  | 2 bedroom | 12
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
C | Matise | New Build | 24 | Studio | 12
|  | available for sale |  | 1 bedroom | 12
|  | Foundation started |  | 2 bedroom | 0
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
D | Degas | New build | 6 | Studio | 2
|  | Hold not released |  | 1 bedroom | 2
|  | foundation started |  | 2 bedroom | 2
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
E | Delacroix | NEw build | 10 | Studio | 4
|  | Hold not released |  | 1 bedroom | 4
|  | Foundation started |  | 2 bedroom | 2
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
F | Gaugin | New Build | 24 | Studio | 12
|  | Foundation completed building upwards |  | 1 bedroom | 12
|  | Available for sale |  | 2 bedroom | 0
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
G | Duchamp | New build | 12 | Studio | 0
|  | Hold not released |  | 1 bedroom | 0
|  | Foundation started |  | 2 bedroom | 12
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
H | Cezanne | New build | 12 | Studio | 0
|  | SOLD |  | 1 bedroom | 0
|  | foundation started |  | 2 bedroom | 12
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
J | Bonheur | new build | 10 | Studio | 4
|  | Hold not released |  | 1 bedroom | 4
|  | foundation started |  | 2 bedroom | 2
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
K | Gercault | new build | 12 | Studio | 0
|  | Hold not released |  | 1 bedroom | 0
|  | foundation started |  | 2 bedroom | 12
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
L | Benoist | New build | 36 | Studio | 18
|  | Hold not released |  | 1 bedroom | 18
|  | foundation started |  | 2 bedroom | 0
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
M | Morisot | new build | 11 | Studio | 5
|  | Hold not released |  | 1 bedroom | 0
|  | foundation started |  | 2 bedroom | 5
|  |  |  | 3 bedroom | 1
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
N | Le Brun | New build Pre-construction | 7 | Studio | 3
|  | Available for sale |  | 1 bedroom | 0
|  |  |  | 2 bedroom | 3
|  |  |  | 3 bedroom | 1
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
O | Fragonard | Pre-construction | 16 | Studio | 6
|  | Hold not released |  | 1 bedroom | 0
|  |  |  | 2 bedroom | 10
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
P | Poussin | Pre-construction | 12 | Studio | 6
|  | Hold not released |  | 1 bedroom | 0
|  |  |  | 2 bedroom | 6
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
Q | Courbet | Pre-construction | 11 | Studio | 5
|  | Hold not released |  | 1 bedroom | 0
|  |  |  | 2 bedroom | 5
|  |  |  | 3 bedroom | 1
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
R | Rodin | Pre-construction | 7 | Studio | 3
|  | Hold not released |  | 1 bedroom | 0
|  |  |  | 2 bedroom | 3
|  |  |  | 3 bedroom | 1
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
S | Seurat | Pre-construction | 12 | Studio | 6
|  | Hold not released |  | 1 bedroom | 0
|  |  |  | 2 bedroom | 6
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
T | Toulouse-Lautrec | New build Pre-construction | 11 | Studio | 5
|  | Available for sale |  | 1 bedroom | 0
|  |  |  | 2 bedroom | 5
|  |  |  | 3 bedroom | 1
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
U | Rousseau | Pre-construction | 11 | Studio | 5
|  | Hold not released |  | 1 bedroom | 0
|  |  |  | 2 bedroom | 5
|  |  |  | 3 bedroom | 1
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
V | Braque | Pre-construction | 7 | Studio | 3
|  | Hold not released |  | 1 bedroom | 0
|  |  |  | 2 bedroom | 3
|  |  |  | 3 bedroom | 1
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Treehouse | 0
TH | Forest Villas | Groundworks and access roads started | 5 | Studio | 0
|  | Available for sale |  | 1 bedroom | 0
|  | new builds |  | 2 bedroom | 0
|  |  |  | 3 bedroom | 0
|  |  |  | 3 bedroom semi detached | 0
|  |  |  | 4 bedroom semi detached | 0
|  |  |  | Forest villas | 5
330
|  |  |  | studio | 109
|  |  |  | 1 bed | 62
|  |  |  | 2 bed | 138
|  |  |  | 3 bed | 15
|  |  |  | 4 bed | 1
|  |  |  | Forest villas | 5
330